## Master Plan
MASTER PLAN
NO | TASKS | STATUS | ASSIGNEE | DEADLINE | DOCUMENT
1 | Introduction | Completed | Oanh | 2026-08-03 | 01. SLDS - SRS_Smart_Logistics_Dispatch_Hub_Routing.docx
2 | Bối cảnh dự án, tham khảo | Completed | Nhung | 2026-08-03 | 01. SLDS - SRS_Smart_Logistics_Dispatch_Hub_Routing.docx
3 | Business Process Current | Completed | Nhung | 2026-08-03 | 03. SLDS - Business Process Curent.pdf
4 | Business Process Propose | Completed | Khoa | 2026-08-03 | 04. SLDS - Business Process Propose.pdf
5 | UCS Diagram | Completed | Oanh | 2026-08-03 | 05. SLDS - Use Case Diagram.pdf
6 | UCS description | Completed | Khoa | 2026-08-03 | 06. SLDS - Use Case Description.pdf
7 | Activity diagram | Completed | Khoa | 2026-08-03 | 07. SLDS_Activity Diagram.pdf
8 | Mockup and prototype | Completed | Minh | 2026-08-03 | https://face-id-scan-verify.lovable.app/
9 | Kiểu dữ liệu | Completed | Minh | 2026-08-03 | 09. SLDS - Kiểu dữ liệu.pdf
10 | Functional Requirement & Non Functional Requirement | Completed | Minh | 2026-08-03 | 10. SLDS - Functional Requirement & Non Functional Requirement.pdf
11 | Slide thuyết trình | Completed | Nhung | 2026-08-03 | https://canva.link/90i5jve1i9mbnfo